AMRITA VISHWA VIDYAPEETHAM

AMRITA SCHOOL OF ENGINEERING

DEPARTMENT OF CSE

15CSE411 Software Project Management

TUTORIAL 3

Marks : 10

*Activities*

|  |  |  |  |
| --- | --- | --- | --- |
| No | Activity | Duration | Predecessor |
| 1 | HW selection | 6 | - |
| 2 | SW design | 4 | - |
| 3 | Install HW | 3 | 1 |
| 4 | Build | 4 | 2 |
| 5 | Documentation | 5 | - |
| 6 | Train user | 3 | 5 |
| 7 | Install & Test | 2 | 3,4,5 |

Develop

(a)Network diagram

(b) Gantt Chart

© What is the project finish date?